## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design
Develop iOS Compatible Mobile App |  | Develop iOS Compatible Mobile App
Develop Android Compatible Mobile App |  | Develop Android Compatible Mobile App
Develop Web Portal application | Develop Web Portal application
Upgrade Database |  |  |  | Upgrade Database
Security Update |  | Security Update
Manual Importing |  |  | Manual Importing
Automated Integration for Importing |  |  | Automated Integration for Importing
Mobile App User Interface Refinement |  |  |  | Mobile App User Interface Refinement
Authentication- Login/Logout | Authentication- Login/Logout
Basic Dashboard with heatmap display |  | Basic Dashboard with heatmap display
Basic Data Searching Capability | Basic Data Searching Capability
Automated Amber Alerts |  |  | Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities |  |  |  | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports | User Based Preferences- Save Search & Reports
Web Portal Redesign |  |  |  | Web Portal Redesign
Export CSV of Reported Data |  |  | Export CSV of Reported Data
Send Manual Amber Alerts by Region |  | Send Manual Amber Alerts by Region
Web Report of Data (View only no Export) |  | Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients |  |  | In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
Doctor | add the name of patients I have treated | I can add treatments | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | I want to be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low
System Administrator | get instant access to all the data | I can ensure data intergity and security | As a System Administrator I can get instant access to all the data so that I can ensure data intergity and security. | - auto updates - task automation options
Pharmaceutical Company | get the latest updates on cases | I can update my inventory count | As a Pharmaceutical Company I can get the latest updates on cases so that I can update my inventory count. | - User name and email address required - only read access
Patient | view a real time dashboard analytics that contains cases globally | I can constantly track the global and local viral cases | As a Patient I can view a real time dashboard analytics that contains cases globally so that I can constantly track the global and local viral cases . | - First and Last Name required - only has read access
Test Center | view a real time dashboard that updates me on both cases and a visual view of supply chain | I can prepare my team for logistical needs in a systematic way | As a Test Center I can view a real time dashboard that updates me on both cases and a visual view of supply chain so that I can prepare my team for logistical needs in a systematic way . | - Only has read access - only maximum 5 dashboards
System Administrator | upgrade the security settings automatically | prevent any form of malicious attacks that could cause privacy & security breaches and fraud | As a System Administrator I can upgrade the security settings automatically so that prevent any form of malicious attacks that could cause privacy & security breaches and fraud. | - Allows full rights to the system - allows 3rd party platforms( ElasticSearch, Grafana, etc) to be used
Doctor | input data into the system database | to further aid in the upgrading of data | As a Doctor I can input data into the system database so that to further aid in the upgrading of data . | - Access rights are limited to certain factors of the database , - allows for a customizable set of metrics for dashboard
Medical Examiner | have a direct messaging system with doctors and healthcare company | I can ensure that tallying regarding deaths are totally valid & legit | As a Medical Examiner I can have a direct messaging system with doctors and healthcare company so that I can ensure that tallying regarding deaths are totally valid & legit . | - Only has read rights to the system - allows to send messaging alerts - system notifies user of updates
Patient | customize the dashboard settings to my preferences | I can have a clearer view of the details that I want to see | As a Patient I can customize the dashboard settings to my preferences so that I can have a clearer view of the details that I want to see . | - Updating of the dashboard is limited to his/her personal details - can change the levels of details & granularity -updates users of software upgrades
Pharmaceutical Company | access a real time analytics view of cases | have a deeper knowledge of how certain drugs would be needed to aid in various cituations. | As a Pharmaceutical Company I can access a real time analytics view of cases so that have a deeper knowledge of how certain drugs would be needed to aid in various cituations.. | - can update a drug recommendation and update drug info on database - send automated messages to stakeholders upon request
Doctor | access any patient's data within the database | I can have advanced knowledge should a patient be under my care & guidance | As a Doctor I can access any patient's data within the database so that I can have advanced knowledge should a patient be under my care & guidance. | - User can not fully update personal details of the patient without - can request secondary backup of data consent - notifies users of potential outbreaks & news related topics
System Administrator | have automatic access to a cloud platform | I can easily migrate data & other features in terms of power outages within the on premises infrastructure | As a System Administrator I can have automatic access to a cloud platform so that I can easily migrate data & other features in terms of power outages within the on premises infrastructure. | - Allows constant monitoring & security upgrades - can give instant access rights on specific emergency situations
Test Center | add details to the materials database | I have a 'bird's overview of the supply and logistics needs | As a Test Center I can add details to the materials database so that I have a 'bird's overview of the supply and logistics needs . | - access rights only allowed to products that are necessary for the test company - send customaizable emails with specific logo & analytical tools
Healthcare Company | access and administer an internal databse of supply & logistics | always be updated on the required materials. | As a Healthcare Company I can access and administer an internal databse of supply & logistics so that always be updated on the required materials.. | - username and secondary email required , - maximum 5 updates daily
Healthcare Company | access a specialized app and internal link | send updated alerts to employees and medical professionals | As a Healthcare Company I can access a specialized app and internal link so that send updated alerts to employees and medical professionals. | - unlimiteded notifications are allowed -full access and rights only given to this specific app & database
Medical Examiner | customize my own analytics dashboard | send real time updates to all involved stakeholders within a given scenario | As a Medical Examiner I can customize my own analytics dashboard so that send real time updates to all involved stakeholders within a given scenario. | - 2 factor authentication is required - can only customize the dashboard specific to their accounts
CDC Official | contact directly an on-call system admin | if there is an immediate power outage or tecfhnical glitch, I am confident that I can update the necessary stakeholders. | As a CDC Official I can contact directly an on-call system admin so that if there is an immediate power outage or tecfhnical glitch, I am confident that I can update the necessary stakeholders.. | - multi-factor authentication (MFA) is also required - limited amount of messaging is allowed due to security reasons - notifies user of pnews related to virus outbreak
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 1 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 1 (MVP) | 4 | 2 Total Stories = 4 | 4
Doctor | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 1 (MVP) | 4 | 3 Total Stories = 3 | 3
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | Release 1 (MVP) | 1 | 4 Total Stories = 5 |  | 4
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered | Release 2 | 3 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password | Release 1 (MVP) | 2 | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 1 (MVP) | 2 | 7 Total Stories = 3 |  |  | 2
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | Release 2 | 2 | Sum | 10 | 9 | 4
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 2 | 2 | Total | 10 | 10 | 5 | 1
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | Release 2 | 3 | SUM = TOTAL | #NAME? | #NAME? | #NAME?
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 2 | 3
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | Backlog for Future Release | 6
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 2 | 4
Test Center | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | - System notifies user by email - User can set number that stock must reach for email to be sent - System notifies user upon login that stock is low | Release 2 | 1
CDC Official | As a CDC Official I can get auotmated emails & warnings regarding logistical issues, so that there will never be an issue of supply deficiciencies . | User gets 'warning emails' if there is an upcoming shortage of test kit supplies. | Release 2 | 4
Patient | As a patient I can customize all majority if the dashboard details so that it would give me a better picture of both my health condition's update and the global pandemic's metrics | Patient only gets to access his/her personal profile. | Release 2 | 5
Medical Examiner | As a Medical Examiner I can access a near real-time update on number of casualties & recoveries so that I make an updated & detailed report on the number of deaths. | Medical examiner has read access rights only to this dashboard. | Release 2 | 5
System Administrator | As a System Administrator I can move monitor the 'over-health' of the entire system so that I can do the necessary updates & troubleshooting ASAP. | Admin has all the technical rights to the system. No other specific configuration is further required. | Release 3 | 6
Patient | As a Patient I can customize the dashboard settings to my preferences so that I can have a clearer view of the details that I want to see . | - Updating of the dashboard is limited to his/her personal details - can change the levels of details & granularity -updates users of software upgrades | Release 3 | 5
Pharmaceutical Company | As a Pharmaceutical Company I can access a real time analytics view of cases so that have a deeper knowledge of how certain drugs would be needed to aid in various cituations.. | - can update a drug recommendation and update drug info on database - send automated messages to stakeholders upon request | Release 3 | 7
Doctor | As a Doctor I can access any patient's data within the database so that I can have advanced knowledge should a patient be under my care & guidance. | - User can not fully update personal details of the patient without - can request secondary backup of data consent - notifies users of potential outbreaks & news related topics | Release 3 | 5
System Administrator | As a System Administrator I can have automatic access to a cloud platform so that I can easily migrate data & other features in terms of power outages within the on premises infrastructure. | - Allows constant monitoring & security upgrades - can give instant access rights on specific emergency situations | Release 1 (MVP) | 5
Test Center | As a Test Center I can add details to the materials database so that I have a 'bird's overview of the supply and logistics needs . | - access rights only allowed to products that are necessary for the test company - send customaizable emails with specific logo & analytical tools | Release 1 (MVP) | 7
Healthcare Company | As a Healthcare Company I can access and administer an internal databse of supply & logistics so that always be updated on the required materials.. | - username and secondary email required , - maximum 5 updates daily | Release 3
Healthcare Company | As a Healthcare Company I can access a specialized app and internal link so that send updated alerts to employees and medical professionals. | - unlimiteded notifications are allowed -full access and rights only given to this specific app & database | Release 1 (MVP)
Medical Examiner | As a Medical Examiner I can customize my own analytics dashboard so that send real time updates to all involved stakeholders within a given scenario. | - 2 factor authentication is required - can only customize the dashboard specific to their accounts | Release 1 (MVP)
CDC Official | As a CDC Official I can contact directly an on-call system admin so that if there is an immediate power outage or tecfhnical glitch, I am confident that I can update the necessary stakeholders.. | - multi-factor authentication (MFA) is also required - limited amount of messaging is allowed due to security reasons - notifies user of pnews related to virus outbreak
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0
0 | As a I can so that . | 0

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | 2
|  | As a Doctor I can login to the system so that I can enter patient treatment information. | 3
|  | As a Doctor I can add the name of patients I have treated so that I can add treatments . | 3
| Sprint 2 | As a System Administrator I can give access to the system so that users can access,import, share data.. | 5
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 0.5
|  | As a Pharmaceutical Company I can get the latest updates on cases so that I can update my inventory count. | 2
|  | As a Patient I can change my test results so that the system data is accurate. | 0.5
| Sprint 3 | As a Pharmaceutical Company I can get the latest updates on cases so that I can update my inventory count. | 5
|  | As a Doctor I can input data into the system database so that to further aid in the upgrading of data . | 2
|  | As a System Administrator I can have automatic access to a cloud platform so that I can easily migrate data & other features in terms of power outages within the on premises infrastructure. | 1
Release 2 | Sprint 4 | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 5
|  | As a Patient I can change my test results so that the system data is accurate. | 0.5
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 1
|  | As a Patient I can customize the dashboard settings to my preferences so that I can have a clearer view of the details that I want to see . | 1
|  | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | 0.5
| Sprint 5 | As a System Administrator I can have automatic access to a cloud platform so that I can easily migrate data & other features in terms of power outages within the on premises infrastructure. | 1
|  | As a System Administrator I can have automatic access to a cloud platform so that I can easily migrate data & other features in terms of power outages within the on premises infrastructure. | 2
|  | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | 2
|  | As a Test Center I can add details to the materials database so that I have a 'bird's overview of the supply and logistics needs . | 1
|  | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | 3
Release 3 | Sprint 6 | As a Healthcare Company I can reset my password by myself so that that I can login again. . | 3
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 5
| Sprint 7 | As a Patient I can view a real time dashboard analytics that contains cases globally so that I can constantly track the global and local viral cases . | 2
|  | As a Medical Examiner I can have a direct messaging system with doctors and healthcare company so that I can ensure that tallying regarding deaths are totally valid & legit . | 0.5
|  | As a System Administrator I can upgrade the security settings automatically so that prevent any form of malicious attacks that could cause privacy & security breaches and fraud. | 5